## Activity Plan
Roll out planning
INDIA
ACTIVITY PLAN |  |  | Q1 17 | [11 empty] | Q2 17 | [11 empty] | Q3 17 | [11 empty] | Q4 17
|  |  | Apr |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar
Focus Area | Deliverables | Action Items | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Network Expansion | Signup institutes & Ecells | Institue sign-ups
Offloading non performing institutes
Infrastructure assessment & testing
Faculty selection
Institute Annual planning meetings | bar: May 3 to May 4
Director/Faculty Round Table | bar: May 1 to May 4
Launch of new E-cells & onbaording new team members to existing E-cells
H1 Review meetings
Annual review meetings
Program Implementation | Team training | Program Manager training
| Master Trainer training | MT for EEP 1 (100 &101) | bar: May 2
MT for EEP 2(102)
MT for EEP 3(103)
MT for RMs for E-leader program
| EEP | EEP 1: Faculty Program for 100 and 101 | bar: May 3 to May 4
EEP 2: Faculty Program for 102
EEP 3: Faculty Program for 103
Advanced Practicum Training: (Concepts & Facilitation) - MOOCs
| Student training | E-leader training
| Curriculum rollout | Course 100
Course 101
Course 102
Course 103
| Practicum rollout | Basic Practicum
Advanced Practicum
Extended Practicum
| Outlier programs | Vertical specific webinars
Bootcamps
Design Thinking workshops
Market level training - Investor Hunt/Venture Voyage/Startup weekend/Startup internships
| Other programs | SmartE Challenge
Topic based webinar
Certification
Intimation mailer to institutes
LW notifications to students
Monitor, track & update certification status
Issue Certificates
Outcome Tracking | Analysis & reporting of previous years' ventures | Half yearly health check of previous years' ventures
| Reporting current years' outcomes | Tracking progress of ventures created, entrepreneurs created, students joining startups & E leader salary comparitive study
Reward Program | Faculty reward | Half yearly reward for 2 faculty
| E-cells reward | Half yearly reward for 2 E-cells
Events |  | E-week & E-Leader Conclave